## Sheet1
NEO Report Card Schedule
2016 |  |  |  |  | 2017 | [11 empty] | 2018
August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May
organization |  |  | research/ data collection | [8 empty] | writing |  |  |  | prep for release |  | release | promotion and outreach
kick off meeting 8/1 | meeting 8/31 | mtg 10/5 | mtg 11/7 | meetings every other month to review progress | [7 empty] | initial category drafts | executive summaries | final draft complete |  | confirm location, invites
committee formation | additions to committee | guidance from Randy Over | form to ASCE | policy statements review | [6 empty] | review all data | preliminary grades | category drafts complete | peer review |  | promotion and press releases
| contact asce | set tone for meeeting w owners | review agencies /owners to contact | data from ASCE headquarters | [7 empty] | visuals and graphics | recommendations to raise grades |  | price printing, location |  | send to printer
| contact ohio council | define categories to cover | review data sources | hold meetings with owners, stakeholders, collect data | [10 empty] | ASCE Advisory Review
| research previous reports |  |  |  | fundraising
discuss schedule for release